## Consolidated time
Average
Logging in to Spotify
Login page website | 10
Login form in the front end | 4
Form error handling (invalid inputs) | 2
User authentication (oauth) | 3
Request answer | 3
Change in page (error or redirect) | 2.5
Total | 24.5
Spotify Sorting
Website page | 9.5
Playlist information | 4.5
Playlist display | 4
Sorting options | 4
Song addition | 2
Song removal | 2
Song order change | 2
Total | 28
Youtube Utilization
Website/Display page | 8
Youtube panel functionality | 8
Finding Spotify song on youtube | 5
Displaying panel where song is played | 7
Adding youtube songs to mixed playlist | 4
Sorting operations on mixed playlist | 4.5
Total | 36.5
Exporting new/edited playlists back into Spotify
Check if playlist is mixed | 2
Select songs to export | 2
Check if spotify has the youtube songs | 6
Integrate with spotify API | 4.75
Total | 14.75

## Mariana
| Time estimation | Notes
Logging in to Spotify
Login page website | 7 hours | Responsive site
Login form in the front end | 3 hours
Form error handling (invalid inputs) | 1 hour
User authentication (oauth) | 2 hours | Input sanitation
Request answer | 30 min
Change in page (error or redirect) | 30 min
Total | 15 hours
Spotify Sorting
Website page | 7 hours
Playlist information | 3 hours
Playlist display | 2 hours
Sorting options | 2 hours
Song addition | 1 hour | Update array and update display
Song removal | 1 hour | Update array and update display
Song order change | 1 hour | Update array and update display
Total | 17
Youtube Utilization
Website/Display page | 10 hours
Youtube panel functionality | 5 hours
Finding Spotify song on youtube | 4 hours
Displaying panel where song is played | 5 hours
Adding youtube songs to mixed playlist | 3 hours
Sorting operations on mixed playlist | 3 hours
Total | 30
Exporting new/edited playlists back into Spotify
Check if playlist is mixed | 1 hours
Select songs to export | 1 hours
Check if spotify has the youtube songs | 4 hours
Integrate with spotify API | 4 hours
10

## Kyle
Time estimations
Logging in to Spotify
Login page website | 10
Login form in the front end | 4
Form error handling (invalid inputs) | 3
User authentication (oauth) | 2
Request answer | 5
Change in page (error or redirect) | 3
Total | 27
Spotify Sorting
Website page | 7
Playlist information | 5
Playlist display | 7
Sorting options | 6
Song addition | 2
Song removal | 2
Song order change | 2
Total | 31
Youtube Utilization
Website/Display page | 7
Youtube panel functionality | 8
Finding Spotify song on youtube | 5
Displaying panel where song is played | 6
Adding youtube songs to mixed playlist | 5
Sorting operations on mixed playlist | 5
Total | 36
Exporting new/edited playlists back into Spotify
Check if playlist is mixed | 3
Select songs to export | 3
Check if spotify has the youtube songs | 8
Integrate with spotify API | 6
Total | 20

## Kurt
Times estimations
Logging in to Spotify
Login page website | 13
Login form in the front end | 5
Form error handling (invalid inputs) | 2
User authentication (oauth) | 3
Request answer | 3
Change in page (error or redirect) | 3
Total | 29
Spotify Sorting
Website page | 13
Playlist information | 3
Playlist display | 2
Sorting options | 5
Song addition | 3
Song removal | 3
Song order change | 3
Total | 32
Youtube Utilization
Website/Display page | 5
Youtube panel functionality | 10
Finding Spotify song on youtube | 4
Displaying panel where song is played | 10
Adding youtube songs to mixed playlist | 5
Sorting operations on mixed playlist | 5
Total | 39
Exporting new/edited playlists back into Spotify
Check if playlist is mixed | 2
Select songs to export | 2
Check if spotify has the youtube songs | 7
Integrate with spotify API | 5
Total | 16

## Lucas
Time estimations
Logging in to Spotify
Login page website | 10
Login form in the front end | 1
Form error handling (invalid inputs) | 2
User authentication (oauth) | 4
Request answer | 3
Change in page (error or redirect) | 2
Total | 22
Spotify Sorting
Website page | 10
Playlist information | 7
Playlist display | 5
Sorting options | 3
Song addition | 1
Song removal | 1
Song order change | 1
Total | 28
Youtube Utilization
Website/Display page | 9
Youtube panel functionality | 9
Finding Spotify song on youtube | 6
Displaying panel where song is played | 8
Adding youtube songs to mixed playlist | 3
Sorting operations on mixed playlist | 4
Total | 39
Exporting new/edited playlists back into Spotify
Check if playlist is mixed | 2
Select songs to export | 2
Check if spotify has the youtube songs | 5
Integrate with spotify API | 4
Total | 13